## Time
Date | Hours | ID | Comments
2016-06-08 | 1 | 1 | Researched Project Ideas
2016-06-10 | 2 | 1 | Researched Project Ideas
2016-06-12 | 2 | 1 | Researched Project Ideas
2016-06-16 | 0.5 | 0 | Setup Notebook
2016-06-16 | 2.5 | 1
2016-06-18 | 0.5 | 0 | Setup Visual Studio Python
2016-06-18 | 0.5 | 1
2016-06-19 | 2.5 | 0 | Setup Timelog Sheet
2016-06-19 | 1 | 1
2016-06-19 | 0.5 | 11 | Setup Git Repository
2016-06-19 | 1.25 | 2
2016-06-21 | 1 | 3 | Start first section
2016-06-22 | 2.5 | 3 | Almost finished with first section
2016-06-23 | 0.5 | 3 | Finished first section
2016-06-24 | 1.5 | 3 | Worked on section 2
2016-06-26 | 1 | 3 | Downloaded Visual Paradigm and worked to finish section 2
2016-06-26 | 2.5 | 3 | Created Use Cases for System and worked on section 3
2016-06-26 | 0.5 | 5
2016-06-27 | 3.5 | 6 | Began making Gantt Chart - Tried a couple different ways ended up using Excel
2016-06-28 | 1.5 | 6 | Finished Gantt Chart and added current day line
2016-07-02 | 0.5 | 6 | Started writing up information for the project plan
2016-07-02 | 0.5 | 4 | Reviewed my Vision Documented and corrected mistakes
2016-07-03 | 2 | 6 | Worked on the COCOMO of the project and finished section 2
2016-07-04 | 1 | 6 | Finished the last section
2016-07-04 | 0.5 | 8
2016-07-04 | 3 | 9 | Completed the SQA document
2016-07-09 | 2 | 11
2016-07-12 | 2 | 11
2016-07-13 | 0.5 | 7
2016-07-13 | 0.5 | 10
2016-07-13 | 4 | 11 | Got the IDS to read training data from a file and put it into the neural network
2016-07-15 | 1 | 11 | Started testing a modified version of a neural network, had discrepencies when training on lots of data - possibly overtraining on normal packets
2016-07-16 | 4 | 11 | Struggled to get the modified version of the neural network to work, getting floating point buffer overflows due to the size of the floats
2016-07-17 | 1 | 11 | Converting back to the old way and trying something new to get it to work for more data
2016-07-18 | 2 | 11 | Worked on refactoring data reader to handle reading more data for training the neural network properly, having probems with buffer overflows still
2016-07-19 | 4 | 11 | Got the Neural Network working at an average correctness of 92%. The issues for overflows was solved by normalizing the data.
2016-07-20 | 3 | 11 | Tried to understand how best to optimize the training of the neural network, also plotted outcomes
2016-07-22 | 3 | 11 | Worked more on the neural network and cleaned up some code
2016-07-23 | 1.5 | 12 | Began working on the PowerPoint
2016-07-24 | 5 | 12 | Finished the PowerPoint
Phase 2 Start
2016-08-23 | 4 | 32 | Worked on creating a GUI for PyIDS
2016-08-25 | 2 | 31 | Worked on getting TCP/IP packets
2016-08-28 | 1 | 13 | Updated Timelog for Phase 2
2016-08-28 | 2 | 31 | Read TCP/IP RFC and studied headers along with KDData99
2016-08-30 | 4 | 31 | For some reason the python package I was using (scapy) no longer works, looking into using raw sockets
2016-09-05 | 2 | 12 | Prepared for the presentation
2016-09-06 | 1.5 | 12 | Gave presentation
2016-09-11 | 0.5 | 18 | Creted the formal specificaiton in USE
2016-09-11 | 1 | 19 | Began writing the formal specificaiton in USE
2016-09-17 | 0.5 | 14 | Made updates to the Vision Document
2016-09-17 | 0.5 | 16 | Made updates to the Project Plan
2016-09-18 | 3.5 | 19 | Finished writing the formal specification in USE
2016-09-18 | 0.2 | 15
2016-09-18 | 0.2 | 17
2016-09-25 | 1 | 21 | Looked over other Architecture Design Documents and decided on sections
2016-09-25 | 2.5 | 22 | Began creating the diagrams and writing infromation
2016-09-27 | 1 | 22 | Worked on the documentation
2016-09-28 | 1 | 22 | Worked on the documentation
2016-10-01 | 1 | 20
2016-10-02 | 1 | 22 | Worked on documentation
2016-10-08 | 4 | 22 | Finished
2016-10-10 | 1 | 24
2016-10-12 | 1.5 | 23
2016-10-14 | 4 | 25
2016-10-14 | 3 | 27 | Created and wrote technical inspection checklist - decided to have executable prototype inspected
2016-10-15 | 0.5 | 26
2016-10-15 | 0.5 | 28
2016-10-16 | 7 | 29 | One problem noticed - it will be impossible to collect all the data for the KDD99 dataset needed. The KDD99 has duration that a given connection is open. This has been documented and emailed to Dr. Neilsen.
2016-10-17 | 2 | 22 | Updated class diagrams
2016-10-17 | 7 | 29 | Got the program working for an architectural prototype. The network traffic reader can read 10 packets and print out their status according to the neural network.
2016-10-17 | 2.5 | 30 | Finished making presentation
2016-10-18 | 1.5 | 30 | Prepared for the presentation and presented
Phase 3 Start
2016-10-22 | 0.5 | 34 | Setup for Phase 3
2016-10-24 | 0.5 | 48 | Sent requests for inspection
2016-11-12 | 0.5 | 36
2016-11-12 | 2.5 | 37 | Finish the user's manual
2016-11-12 | 0.5 | 39
2016-11-12 | 3.5 | 40 | Created new design and reviewed previous design. Also referenced past materials from CIS 744 for any possible updates.
2016-11-13 | 1 | 52 | Worked on new GUI Design
2016-11-19 | 3 | 35 | Added action item to change percentage
2016-11-20 | 3 | 52 | Developed new GUI for final
2016-11-26 | 5 | 52 | Developed new GUI for final
2016-11-27 | 2 | 52 | Developed new GUI for final
2016-12-03 | 1 | 41
2016-12-03 | 1 | 50 | Reviewed the inspection letters from collegues
2016-12-03 | 0.5 | 48 | Wrote review on inspection letters
2016-12-03 | 2 | 48 | Reviewed Tracy Marshall's project
2016-12-04 | 0.5 | 45
2016-12-04 | 4 | 46 | Worked on graphs and writing up information
2016-12-04 | 0.5 | 42
2016-12-04 | 1 | 49 | Wrote up reference document
2016-12-04 | 0.5 | 53 | Created outline for presentation
2016-12-04 | 0.5 | 38 | Reviewed User Manual and added figures
2016-12-09 | 7 | 52 | Worked on finishing application and cleaning up
2016-12-10 | 1 | 38 | Updated UI pictures and added sections for additional GUI options
2016-12-10 | 2 | 35 | Updated Architecture Design Documents for new features.
2016-12-10 | 2 | 41 | Updated Component Design Document
2016-12-10 | 2.5 | 43 | Wrote Unit Tests and System Test Procedure
2016-12-10 | 0.5 | 42 | Fixed Document Outline
2016-12-10 | 2 | 43 | Updated Document with Test Results
2016-12-11 | 4 | 52 | Cleaned up code and worked on any remainin action items
2016-12-11 | 0.5 | 44 | Review Assessment and rested to ensure correctness
2016-12-11 | 1 | 47 | Updated documents with latest figures
2016-12-11 | 3 | 53 | Went over everything and made presentation

## Tasks
Name | Status | ID | Epic Item | Estimate (hrs) | Remaining (hrs) | Completed (hrs) | Progress
Setup | DONE | 0 | Setup | 3 | 0 | 3.5 | 100%
Research | DONE | 1 | Research | 6 | 0 | 9 | 100%
Create Vision Document | DONE | 2 | Vision Document | 1 | 0 | 1.25 | 100%
Write Vision Document | DONE | 3 | Vision Document | 10 | 0 | 9 | 100%
Review Vision Document | DONE | 4 | Vision Document | 2 | 0 | 0.5 | 100%
Create Project Plan | DONE | 5 | Project Plan Document | 1 | 0 | 0.5 | 100%
Write Project Plan | DONE | 6 | Project Plan Document | 10 | 0 | 8.5 | 100%
Review Project Plan | DONE | 7 | Project Plan Document | 2 | 0 | 0.5 | 100%
Create SQA Plan | DONE | 8 | SQA Plan Document | 1 | 0 | 0.5 | 100%
Write SQA Plan | DONE | 9 | SQA Plan Document | 10 | 0 | 3 | 100%
Review SQA Plan | DONE | 10 | SQA Plan Document | 2 | 0 | 0.5 | 100%
Develop Prototype | DONE | 11 | Prototype | 20 | 0 | 26.5 | 100%
Work on Presentation | DONE | 12 | Presentation | 10 | 0 | 10 | 100%
Update Timelog | DONE | 13 | Setup Phase 2 | 1.5 | 0 | 1 | 100%
Modify Vision Document 2.0 | DONE | 14 | Vision Document 2.0 | 4 | 0 | 0.5 | 100%
Review Vision Document 2.0 | DONE | 15 | Vision Document 2.0 | 1 | 0 | 0.2 | 100%
Modify Project Plan 2.0 | DONE | 16 | Project Plan 2.0 | 4 | 0 | 0.5 | 100%
Review Project Plan 2.0 | DONE | 17 | Project Plan 2.0 | 1 | 0 | 0.2 | 100%
Create Formal Specification | DONE | 18 | Formal Specification | 1 | 0 | 0.5 | 100%
Write Formal Specification | DONE | 19 | Formal Specification | 8 | 0 | 4.5 | 100%
Review Formal Specification | DONE | 20 | Formal Specification | 1 | 0 | 1 | 100%
Create Architecture Design | DONE | 21 | Architecture Design | 2 | 0 | 1 | 100%
Write Architecture Design | DONE | 22 | Architecture Design | 10 | 0 | 11.5 | 100%
Review Architecture Design | DONE | 23 | Architecture Design | 1 | 0 | 1.5 | 100%
Create Test Plan | DONE | 24 | Test Plan | 2 | 0 | 1 | 100%
Write Test Plan | DONE | 25 | Test Plan | 6 | 0 | 4 | 100%
Review Test Plan | DONE | 26 | Test Plan | 1 | 0 | 0.5 | 100%
Writeup Formal Technical Inspection Document | DONE | 27 | Formal Technical Inspection | 4 | 0 | 3 | 100%
Review Formal Technical Document | DONE | 28 | Formal Technical Inspection | 0.5 | 0 | 0.5 | 100%
Develop Architecture Executable | DONE | 29 | Architecture Executable | 15 | 0 | 14 | 100%
Work on Phase 2 Presentation | DONE | 30 | Phase 2 Presentation | 3 | 0 | 4 | 100%
Reseach TCP/IP | DONE | 31 | Reseach | 10 | 0 | 8 | 100%
Reseach GUI | DONE | 32 | Reseach | 4 | 0 | 4 | 100%
Research Neural Network Design | DONE | 33 | Reseach | 0 | 0 | 0 | 0%
Update Timelog | DONE | 34 | Setup Phase 3 | 0.5 | 0 | 0.5 | 100%
Fix Action Items | DONE | 35 | Setup Phase 3 | 3 | 0 | 5 | 100%
Create User Manual | DONE | 36 | User Manual | 1 | 0 | 0.5 | 100%
Write User Manual | DONE | 37 | User Manual | 2 | 0 | 2.5 | 100%
Review User Manual | DONE | 38 | User Manual | 0.5 | 0 | 1.5 | 100%
Create Component Design | DONE | 39 | Component Design | 2 | 0 | 0.5 | 100%
Write Component Design | DONE | 40 | Component Design | 5 | 0 | 3.5 | 100%
Review Component Design | DONE | 41 | Component Design | 1 | 0 | 3 | 100%
Create Assessment Evaluation (Test Report) | DONE | 42 | Assessment Evaluation | 1 | 0 | 1 | 100%
Write Assessment Evaluation (Test Report) | DONE | 43 | Assessment Evaluation | 6 | 0 | 4.5 | 100%
Review Assessment Evaluation (Test Report) | DONE | 44 | Assessment Evaluation | 0.5 | 0 | 0.5 | 100%
Create Project Evaluation | DONE | 45 | Project Evaluation | 0.5 | 0 | 0.5 | 100%
Write Project Evaluation | DONE | 46 | Project Evaluation | 6 | 0 | 4 | 100%
Review Project Evaluation | DONE | 47 | Project Evaluation | 1 | 0 | 1 | 100%
Writeup Formal Technical Inspection Document | DONE | 48 | Technical Inspection | 2 | 0 | 3 | 100%
Create and Write References | DONE | 49 | Technical Inspection | 1 | 0 | 1 | 100%
Review Inspection Letters | DONE | 50 | Technical Inspection | 1.5 | 0 | 1 | 100%
Fix Issues from Insepctions as needed | DONE | 51 | Develop Final Program | 4 | 0 | 0 | 0%
Develop Final Program | DONE | 52 | Develop Final Program | 20 | 0 | 22 | 100%
Create Final Presentation | DONE | 53 | Phase 3 Presentation | 3 | 0 | 3.5 | 100%

## Phase Totals
PHASE 1 |  |  |  | PHASE 1
Epic Items | Completed (hrs) | Remaining (hrs) | Progress | Start Date | Today | End Date | Days In | Days Left | Class Completed | Delta | Delta Days
Setup | 3.5 | 0 | 100% | 2016-06-06 | 2016-07-29 | 2016-07-29 | 53 | 0 | 100% | 0% | 0
Research | 9 | 0 | 100%
Vision Document | 10.75 | 0 | 100%
Project Plan Document | 9.5 | 0 | 100%
SQA Plan Document | 4 | 0 | 100%
Prototype | 26.5 | 0 | 100%
Presentation | 10 | 0 | 100%
Misc. | 0 | 0 | 0%
Total | 73.25 | 0 | 100%
PHASE 2 |  |  |  | PHASE 2
Epic Items | Completed (hrs) | Remaining (hrs) | Progress | Start Date | Today | End Date | Days In | Days Left | Class Completed | Delta | Delta Days
Setup Phase 2 | 1 | 0 | 100% | 2016-08-22 | 2016-10-19 | 2016-10-19 | 58 | 0 | 100% | 0% | 0
Vision Document 2.0 | 0.7 | 0 | 100%
Project Plan 2.0 | 0.7 | 0 | 100%
Formal Specification | 6 | 0 | 100%
Architecture Design | 14 | 0 | 100%
Test Plan | 5.5 | 0 | 100%
Formal Technical Inspection | 3.5 | 0 | 100%
Architecture Executable | 14 | 0 | 100%
Phase 2 Presentation | 4 | 0 | 100%
Reseach | 12 | 0 | 100%
Total | 61.4 | 0 | 100%
PHASE 3 |  |  |  | PHASE 3
Epic Items | Completed (hrs) | Remaining (hrs) | Progress | Start Date | Today | End Date | Days In | Days Left | Class Completed | Delta | Delta Days
Setup Phase 3 | 5.5 | 0 | 100% | 2016-10-19 | 2016-12-10 | 2016-12-13 | 52 | 3 | 94.55% | 5.455% | 3
User Manual | 4.5 | 0 | 100%
Component Design | 7 | 0 | 100%
Assessment Evaluation | 6 | 0 | 100%
Project Evaluation | 5.5 | 0 | 100%
Technical Inspection | 5 | 0 | 100%
Develop Final Program | 22 | 0 | 100%
Phase 3 Presentation | 3.5 | 0 | 100%
Total | 59 | 0 | 100%
Total |  |  |  | Total
Epic Items | Completed (hrs) | Remaining (hrs) | Progress | Start Date | Today | End Date | Days In | Days Left | Class Completed | Delta | Delta Days
Setup | 3.5 | 0 | 100% | 2016-06-06 | 2016-12-10 | 2016-12-13 | 187 | 3 | 98.42% | 1.579% | 3
Research | 9 | 0 | 100%
Vision Document | 10.75 | 0 | 100%
Project Plan Document | 9.5 | 0 | 100%
SQA Plan Document | 4 | 0 | 100%
Prototype | 26.5 | 0 | 100%
Presentation | 10 | 0 | 100%
Misc. | 0 | 0 | 0%
Setup Phase 2 | 1 | 0 | 100%
Vision Document 2.0 | 0.7 | 0 | 100%
Project Plan 2.0 | 0.7 | 0 | 100%
Formal Specification | 6 | 0 | 100%
Architecture Design | 14 | 0 | 100%
Test Plan | 5.5 | 0 | 100%
Formal Technical Inspection | 3.5 | 0 | 100%
Architecture Executable | 14 | 0 | 100%
Phase 2 Presentation | 4 | 0 | 100%
Reseach | 12 | 0 | 100%
Setup Phase 3 | 5.5 | 0 | 100%
User Manual | 4.5 | 0 | 100%
Component Design | 7 | 0 | 100%
Assessment Evaluation | 6 | 0 | 100%
Project Evaluation | 5.5 | 0 | 100%
Technical Inspection | 5 | 0 | 100%
Develop Final Program | 22 | 0 | 100%
Phase 3 Presentation | 3.5 | 0 | 100%
Total | 193.65 | 0 | 100%

## Estimates and Graphs
| SLOC | Time (months) |  | Phase | Percent of Time
Estimate | 4000 | 6.59 |  | Phase 1 | 37.83%
Final | 1172 | 6.3333 |  | Phase 2 | 31.71%
Accuracy | 29.3% | 96.11% |  | Phase 3 | 30.47%
Phase | Estimate | Actual | Percent
Phase 1 | 78 | 73.25 | 93.91%
Phase 2 | 80 | 61.4 | 76.75%
Phase 3 | 61.5 | 59 | 95.93%