## Time
Date | Hours | ID | Comments
2016-06-08 | 1 | 1 | Researched Project Ideas
2016-06-10 | 2 | 1 | Researched Project Ideas
2016-06-12 | 2 | 1 | Researched Project Ideas
2016-06-16 | 0.5 | 0 | Setup Notebook
2016-06-16 | 2.5 | 1
2016-06-18 | 0.5 | 0 | Setup Visual Studio Python
2016-06-18 | 0.5 | 1
2016-06-19 | 2.5 | 0 | Setup Timelog Sheet
2016-06-19 | 1 | 1
2016-06-19 | 0.5 | 11 | Setup Git Repository
2016-06-19 | 1.25 | 2
2016-06-21 | 1 | 3 | Start first section
2016-06-22 | 2.5 | 3 | Almost finished with first section
2016-06-23 | 0.5 | 3 | Finished first section
2016-06-24 | 1.5 | 3 | Worked on section 2
2016-06-26 | 1 | 3 | Downloaded Visual Paradigm and worked to finish section 2
2016-06-26 | 2.5 | 3 | Created Use Cases for System and worked on section 3
2016-06-26 | 0.5 | 5
2016-06-27 | 3.5 | 6 | Began making Gantt Chart - Tried a couple different ways ended up using Excel
2016-06-28 | 1.5 | 6 | Finished Gantt Chart and added current day line
2016-07-02 | 0.5 | 6 | Started writing up information for the project plan
2016-07-02 | 0.5 | 4 | Reviewed my Vision Documented and corrected mistakes
2016-07-03 | 2 | 6 | Worked on the COCOMO of the project and finished section 2
2016-07-04 | 1 | 6 | Finished the last section
2016-07-04 | 0.5 | 8
2016-07-04 | 3 | 9 | Completed the SQA document
2016-07-09 | 2 | 11
2016-07-12 | 2 | 11
2016-07-13 | 0.5 | 7
2016-07-13 | 0.5 | 10
2016-07-13 | 4 | 11 | Got the IDS to read training data from a file and put it into the neural network
2016-07-15 | 1 | 11 | Started testing a modified version of a neural network, had discrepencies when training on lots of data - possibly overtraining on normal packets
2016-07-16 | 4 | 11 | Struggled to get the modified version of the neural network to work, getting floating point buffer overflows due to the size of the floats
2016-07-17 | 1 | 11 | Converting back to the old way and trying something new to get it to work for more data
2016-07-18 | 2 | 11 | Worked on refactoring data reader to handle reading more data for training the neural network properly, having probems with buffer overflows still
2016-07-19 | 4 | 11 | Got the Neural Network working at an average correctness of 92%. The issues for overflows was solved by normalizing the data.
2016-07-20 | 3 | 11 | Tried to understand how best to optimize the training of the neural network, also plotted outcomes
2016-07-22 | 3 | 11 | Worked more on the neural network and cleaned up some code
2016-07-23 | 1.5 | 12 | Began working on the PowerPoint
2016-07-24 | 5 | 12 | Finished the PowerPoint
2016-08-23 | 4 | 32 | Worked on creating a GUI for PyIDS
2016-08-25 | 2 | 31 | Worked on getting TCP/IP packets
2016-08-28 | 1 | 13 | Updated Timelog for Phase 2
2016-08-28 | 2 | 31 | Read TCP/IP RFC and studied headers along with KDData99
2016-08-30 | 4 | 31 | For some reason the python package I was using (scapy) no longer works, looking into using raw sockets
2016-09-05 | 2 | 12 | Prepared for the presentation
2016-09-06 | 1.5 | 12 | Gave presentation
2016-09-11 | 0.5 | 18 | Creted the formal specificaiton in USE
2016-09-11 | 1 | 19 | Began writing the formal specificaiton in USE
2016-09-17 | 0.5 | 14 | Made updates to the Vision Document
2016-09-17 | 0.5 | 16 | Made updates to the Project Plan
2016-09-18 | 3.5 | 19 | Finished writing the formal specification in USE
2016-09-18 | 0.2 | 15
2016-09-18 | 0.2 | 17
2016-09-25 | 1 | 21 | Looked over other Architecture Design Documents and decided on sections
2016-09-25 | 2.5 | 22 | Began creating the diagrams and writing infromation
2016-09-27 | 1 | 22 | Worked on the documentation
2016-09-28 | 1 | 22 | Worked on the documentation
2016-10-01 | 1 | 20
2016-10-02 | 1 | 22 | Worked on documentation
2016-10-08 | 4 | 22 | Finished
2016-10-10 | 1 | 24
2016-10-12 | 1.5 | 23
2016-10-14 | 4 | 25
2016-10-14 | 3 | 27 | Created and wrote technical inspection checklist - decided to have executable prototype inspected
2016-10-15 | 0.5 | 26
2016-10-15 | 0.5 | 28
2016-10-16 | 7 | 29 | One problem noticed - it will be impossible to collect all the data for the KDD99 dataset needed. The KDD99 has duration that a given connection is open. This has been documented and emailed to Dr. Neilsen.
2016-10-17 | 2 | 22 | Updated class diagrams
2016-10-17 | 7 | 29 | Got the program working for an architectural prototype. The network traffic reader can read 10 packets and print out their status according to the neural network.
2016-10-17 | 2.5 | 30 | Finished making presentation

## Tasks
Name | Status | ID | Epic Item | Estimate (hrs) | Remaining (hrs) | Completed (hrs) | Progress
Setup | DONE | 0 | Setup | 3 | 0 | 3.5 | 100%
Research | DONE | 1 | Research | 6 | 0 | 9 | 100%
Create Vision Document | DONE | 2 | Vision Document | 1 | 0 | 1.25 | 100%
Write Vision Document | DONE | 3 | Vision Document | 10 | 0 | 9 | 100%
Review Vision Document | DONE | 4 | Vision Document | 2 | 0 | 0.5 | 100%
Create Project Plan | DONE | 5 | Project Plan Document | 1 | 0 | 0.5 | 100%
Write Project Plan | DONE | 6 | Project Plan Document | 10 | 0 | 8.5 | 100%
Review Project Plan | DONE | 7 | Project Plan Document | 2 | 0 | 0.5 | 100%
Create SQA Plan | DONE | 8 | SQA Plan Document | 1 | 0 | 0.5 | 100%
Write SQA Plan | DONE | 9 | SQA Plan Document | 10 | 0 | 3 | 100%
Review SQA Plan | DONE | 10 | SQA Plan Document | 2 | 0 | 0.5 | 100%
Develop Prototype | DONE | 11 | Prototype | 20 | 0 | 26.5 | 100%
Work on Presentation | DONE | 12 | Presentation | 10 | 0 | 10 | 100%
Update Timelog | DONE | 13 | Setup Phase 2 | 1.5 | 0 | 1 | 100%
Modify Vision Document 2.0 | DONE | 14 | Vision Document 2.0 | 4 | 0 | 0.5 | 100%
Review Vision Document 2.0 | DONE | 15 | Vision Document 2.0 | 1 | 0 | 0.2 | 100%
Modify Project Plan 2.0 | DONE | 16 | Project Plan 2.0 | 4 | 0 | 0.5 | 100%
Review Project Plan 2.0 | DONE | 17 | Project Plan 2.0 | 1 | 0 | 0.2 | 100%
Create Formal Specification | DONE | 18 | Formal Specification | 1 | 0 | 0.5 | 100%
Write Formal Specification | DONE | 19 | Formal Specification | 8 | 0 | 4.5 | 100%
Review Formal Specification | DONE | 20 | Formal Specification | 1 | 0 | 1 | 100%
Create Architecture Design | DONE | 21 | Architecture Design | 2 | 0 | 1 | 100%
Write Architecture Design | DONE | 22 | Architecture Design | 10 | 0 | 11.5 | 100%
Review Architecture Design | DONE | 23 | Architecture Design | 1 | 0 | 1.5 | 100%
Create Test Plan | DONE | 24 | Test Plan | 2 | 0 | 1 | 100%
Write Test Plan | DONE | 25 | Test Plan | 6 | 0 | 4 | 100%
Review Test Plan | DONE | 26 | Test Plan | 1 | 0 | 0.5 | 100%
Writeup Formal Technical Inspection Document | DONE | 27 | Formal Technical Inspection | 4 | 0 | 3 | 100%
Review Formal Technical Document | DONE | 28 | Formal Technical Inspection | 0.5 | 0 | 0.5 | 100%
Develop Architecture Executable | DONE | 29 | Architecture Executable | 15 | 0 | 14 | 100%
Work on Phase 2 Presentation | DONE | 30 | Phase 2 Presentation | 3 | 0 | 2.5 | 100%
Reseach TCP/IP | DONE | 31 | Reseach | 10 | 0 | 8 | 100%
Reseach GUI | DONE | 32 | Reseach | 4 | 0 | 4 | 100%
Research Neural Network Design | DONE | 33 | Reseach | 0 | 0 | 0 | 0%

## Phase Totals
PHASE 1 |  |  |  | PHASE 1
Epic Items | Completed (hrs) | Remaining (hrs) | Progress | Start Date | Today | End Date | Days In | Days Left | Class Completed | Delta | Delta Days
Setup | 3.5 | 0 | 100% | 2016-06-06 | 2016-07-29 | 2016-07-29 | 53 | 0 | 100% | 0% | 0
Research | 9 | 0 | 100%
Vision Document | 10.75 | 0 | 100%
Project Plan Document | 9.5 | 0 | 100%
SQA Plan Document | 4 | 0 | 100%
Prototype | 26.5 | 0 | 100%
Presentation | 10 | 0 | 100%
Misc. | 0 | 0 | 0%
Total | 73.25 | 0 | 100%
PHASE 2 |  |  |  | PHASE 2
Epic Items | Completed (hrs) | Remaining (hrs) | Progress | Start Date | Today | End Date | Days In | Days Left | Class Completed | Delta | Delta Days
Setup Phase 2 | 1 | 0 | 100% | 2016-08-22 | 2016-10-17 | 2016-10-19 | 56 | 2 | 96.55% | 3.448% | 2
Vision Document 2.0 | 0.7 | 0 | 100%
Project Plan 2.0 | 0.7 | 0 | 100%
Formal Specification | 6 | 0 | 100%
Architecture Design | 14 | 0 | 100%
Test Plan | 5.5 | 0 | 100%
Formal Technical Inspection | 3.5 | 0 | 100%
Architecture Executable | 14 | 0 | 100%
Phase 2 Presentation | 2.5 | 0 | 100%
Reseach | 12 | 0 | 100%
Total | 59.9 | 0 | 100%